Project name
Electrocardiogram research and development
Fellows
Tarek Loubani, Luka Mustafa
Project update
The project has advanced significantly since work began with IRNAS. At this point, we have completed a significant part of the electronics of the electrocardiogram.
Current prototypes are still not usable. Regulatory approval is still under way, but we haven’t yet received permission from Health Canada to use test our hardware on human subjects in our calibration and validation trials.
The time and cost overruns are multi-factorial, including overestimating the progress of the pre-existing electrocardiogram design and difficulties in navigating regulatory hurdles.
Proposed changes
We have already overrun our budget, but have not yet completed engineering on the electrocardiogram. We would like IRNAS to continue mechanical and electronics work until completion and believe that we have a much better idea of what this would require now. The main change in this proposal is the budget and time given to the engineering side of the project.

In terms of budget, we would like to increase the budget by USD$ 40,000 for engineering. This would be divided as follows. This table assumes that € 1 = USD$ 1.25, and that the cost per hour will remain as quoted by IRNAS as € 45.00:

	Hours	Total (€)
Firmware development	80	3,840.00
Digital filters adjustment and testing	150	7,200.00
Filter testing at the simulation center	20	960.00
Firmware and Android app optimization	40	1,920.00
PCB Redesign	80	3,840.00
External medical certification training and consultancy	-	1,670
Total	370	19,430.00

In terms of time, we request an extension of the completion date from October 2018 as presently approved until December 2019. This should account for any delays in engineering as well as regulatory approval.
Opportunity associated with change
The electrocardiogram is currently still unusable. This proposed change would allow us to complete the final parts of the engineering so that the device is usable.
Risk associated with change
If forced to leave the electrocardiogram as is, we would contribute it to the literature and body of knowledge. Our excellent documentation and use of open source techniques makes our work a significant advancement that other groups could build upon.
However, the electrocardiogram would not be clinically useful in its current state, since it has not completed its engineering phase. Its use in clinical settings would be uncertain.
I fear that these limitations would so limit the electrocardiogram that a competent governmental buyer might overlook the value of the open source construction and potential to select other units that can be used out of the box.
Budget effect of change
This proposed change would increase the budget of this project by USD$ 40,000, paid to IRNAS. This amount would include some of the monies already paid to IRNAS from the Glia portion of the budget over the past several months.
Action required
No further action is required if this change is approved, as all relationships and contracts already exist and allow for cost overruns.