Project name
Canadian Office Project Manager – 2020-2024
Fellow(s)
Tarek Loubani
Date
August 28, 2019
Project description
To provide a project manager who will manage the administrative and financial tasks of the team.
General report-back
Carrie Wakem was hired for the position of project manager. Her work spanned several other informal roles, including accounting, administrative, and community management. During the first year, she was able to orient herself with the project and contributed tremendously to the progress of the Glia team.
During this project, we planned a sustainable transition for the Project Manager to become an independently funded position. The Project Manager role is expected to be filled by Carrie Wakem, who will continue maintaining the project’s task boards, communication tools, project financials, meeting minutes, and other administrative tools. During this period, the Glia team will also pursue several revenue generation strategies to gradually taper the Shuttleworth Foundation contribution and replace them with sustainable funding.
Deliverables achieved
The following deliverables continued to be achieved:
- Annual tax filings (in collaboration with accountant)
- Annual Science Research and Experimental Development (SRED) filing with Canadian Revenue Agency (CRA) to facilitate tax incentive for salary paid to Tarek Loubani
- Twice-yearly report on activities and successes
- Rapid minutes for each meeting
- Management of kanban-style task board (e.g., with kanboard) of team's tasks
- Leadership role in remote offices
- Contribution to device development
- Successful community management
- Overall team leadership
- Transition to sustainable funding
Deliverables not achieved
We aimed to hire a community manager to replace Carrie in that role, but this has not yet happened.
Measures of success
Did you see changes in behaviour that you expected to see?
1. The group was able to work more cohesively and efficiently
2. The PM was able to more quickly identify blocking issues and barriers to progress in the overall projects. While this was a huge improvement in the project's overall progress, it could have been optimized further – and it was in future
3. Financial reports and tax filings were completed easily and on time for this project year. Maintaining this was essential to the health of the project.
4. Better maintained administrative life
5. Carrie stepping into the community management role and developing her leadership skills
Did you see changes in behaviour that you would have liked to see?
NA
Did you see changes in behaviour that you would have loved to see?
NA
Budget
	Canadian (CAD$)	American (USD$)
Approved budget	165,000	122,100.00
Actual spend	165,000	124,310.62
Difference	0	- 2,210.62

Comparison and feedback: Overspend by $2,210.62 was due to forex difference.
Intellectual property outputs
NA
Learnings
The role of the Project Manager went as planned for the third year. The PM continued in her supportive role to our remote office. She also facilitated the project’s financials, calendar, task board and overall team communication.
The biggest learning of this year happened in transitioning Carrie from an administrative role to a leadership role. This involved trust between the project and Carrie, and taking on responsibilities that are not simply more work, but more leadership.
This leadership will facilitate the breakdown of the role into other administrative and management roles as the project grows and attracts more people.
Exit/Sustainability/Viability
With revenue generation developing, this project will end with no dependence on the Shuttleworth Foundation for Project Manager funding.
Conclusion
It is expected that the PM will continue to grow in her role in the next few years, and that the position will become financially self-sufficient.
Next steps
At the end of 2024, we will re-evaluate this position and its funding to assess success as highlighted above.