Project name
Canadian Office Project Manager - 2018
Fellow(s)
Tarek Loubani
Date
August 28, 2019
Project description
To provide a project manager who will manage the administrative and financial tasks of the team.
General report-back
Carrie Wakem was hired for the position of project manager. Her work spanned several other informal roles, including accounting, administrative, and community management. During the first year, she was able to orient herself with the project and contributed tremendously to the progress of the Glia team.
During her second year in the Project Manager role, Carrie Wakem continued maintaining the project’s task boards, communication tools, project financials, meeting minutes, and other administrative tools. During this year, Carrie emerged as a leader in the project, beginning her transition from an administrator to a manager and leader. She started providing leadership and support to our remote office. On the technical side of the project, Carrie was involved in device development and stethoscope production, leading technical (3D printing) workshops. She also transitioned into the Community and Relationship Management roles.
Deliverables achieved
The following deliverables continued to be achieved:
- Annual tax filings (in collaboration with accountant)
- Annual Science Research and Experimental Development (SRED) filing with Canadian Revenue Agency (CRA) to facilitate tax incentive for salary paid to Tarek Loubani
- Twice-yearly report on activities and successes
- Rapid minutes for each meeting
- Management of kanban-style task board (e.g., with kanboard) of team's tasks

New deliverables achieved:
- leadership role in remote offices
- contribution to device development
- learn technical components of 3D printing and production management and educate others in workshop setting
- overall team leadership
- successful community management
Deliverables not achieved
A grant application that we aimed for Carrie to complete could not be completed due to time restrictions and a redirection of the project toward other forms of revenue generation.
Measures of success
Did you see changes in behaviour that you expected to see?
1. The group was able to work more cohesively and efficiently
2. The PM was able to more quickly identify blocking issues and barriers to progress in the overall projects. While this was a huge improvement in the project's overall progress, it could have been optimized further – and it was in future
3. Financial reports and tax filings were completed easily and on time for this project year. Maintaining this was essential to the health of the project.
4. Better maintained administrative life
Did you see changes in behaviour that you would have liked to see?
NA
Did you see changes in behaviour that you would have loved to see?
Carrie stepping into the community management role and developing her leadership skills
Budget
	Canadian (CAD$)	American (USD$)
Approved budget	55,000	40,700.00
Actual spend	55,000	42,327.37
Difference	0	-1,627.37

Comparison and feedback: Overspend by $1,627.37 was due to forex difference.
Intellectual property outputs
NA
Learnings
The role of the Project Manager went as planned for the second year. The PM continued in her supportive role to our remote office. She also facilitated the project’s financials, calendar, task board and overall team communication.
The biggest learning of this year happened in transitioning Carrie from an administrative role to a leadership role. This involved trust between the project and Carrie, and taking on responsibilities that are not simply more work, but more leadership.
This leadership will facilitate the breakdown of the role into other administrative and management roles as the project grows and attracts more people.
Exit/Sustainability/Viability
The Project Manager is expected to continue on for another year.
Conclusion
The Project Manager has achieved all expectations of the role. It is expected that the PM will continue to grow in her role in the next few years.
Next steps
Reinstate contract for Y3.