Project name
Glia Gaza Office
Fellow(s)
Tarek Loubani
Date
August 28, 2019
Project description
To establish a Gaza office that can follow and implement the research work of Glia in Gaza hospitals.
General report-back
The Gaza office of Glia was set up to ensure that knowledge and research developed in the Canadian office would be translated to the field. As well as serving as an acid test of some of the ideas of manufacturing in a third world setting, the Gaza office was ultimately able to create its own research projects, culminating in the creation of the tourniquet and desktop injection molding.
Deliverables achieved
The following deliverables were achieved:
- Setup of a remote office for the Glia project in Gaza
- Setup of solar power for the office
- Hiring of office manager and two engineers
- Implementation of stethoscope project
- Implementation of tourniquet project
- Desktop injection molding
- Creation of 3D printing culture in Gaza
Deliverables not achieved
We have not yet achieved full sustainability of the office in financial terms.
Measures of success
Did you see changes in behaviour that you expected to see?
Did you see changes in behaviour that you would have liked to see?
NA
Did you see changes in behaviour that you would have loved to see?
NA
Budget
	USD$
Approved budget	42,585
Actual spend	45,530
Difference	-2,945

Comparison and feedback: Overspend by $2,210.62 was due to forex difference.
Intellectual property outputs
NA
Learnings

Exit/Sustainability/Viability
With revenue generation developing, this project will end with no dependence on the Shuttleworth Foundation for the Gaza office.
Conclusion

Next steps