## Project Timeline
Project Timeline

	Innovation Fund Year 1				Innovation Fund Year 2
	2018				2019
	Quarterly				Quarterly
project:	First	Second	Third	Fourth	First	Second	Third	Fourth

Pulse Oximeter	Pulse Oximeter: / Phase II
				Pulse Oximeter: / Phase III
					Pulse Oximeter: / Phase IV			Continue to build this network

Project Phases

Phase I:	1. Device Design / 2. Prototype Creation
Phase II:	3. Experimental calibration & validation
Phase III:	4. Health Canada Approval / 5. Publicaion
Phase IV:	6. Assembly Instruction / 7. Knowlege Translation & Product Development/Dissemination