Project name
Glia Website
Fellow(s)
Tarek Loubani
Short description
The Glia project's website was made in an ad hoc fashion. Since then, the project's need for an attractive and representative web presence has increased. This project tackles the creation of the Glia website.
Objective(s)
- To create a website that displays the work our team has already done
- To facilitate volunteer applications and efforts into the team.
- To create a place to recognize previous volunteers and participants
Link to scope of fellowship(s)
The fellowship scope of creating a culture around open medical devices includes the need to communicate with other academics, manufacturers and health care providers. For the past four years, interested parties have communicated with us through high friction methods such as Internet Relay Chat (IRC), email, github and social media. While these methods provided all of the content relevant to our work, they did so in a disparate way.
A website will help us communicate this information to our main audiences: academics, manufacturers and health care providers.
Context
Information about Glia and its work is distributed among many sources, including github repositories, news articles, social media posts, email and Internet Relay Chat (IRC) logs. There exists no easily accessible showcase for our work, nor an easy way for volunteers to connect with our project.
Over the past two decades, websites have emerged as the de facto standard for projects such as ours, housing philosophical and practical information about various projects. While the Glia project does have a website, it is limited and has not been effective.
After discussion with the team, we agreed that there should be a formal and professional effort to bring a website forward by hiring a professional designer.
Intended beneficiaries
- Potential collaborators such as academics, manufacturers and health care providers – These providers understand that Glia can help them, but may not be sure of how to contact the team or what our work entails
- Lay public – Through media exposure, the lay public may be interested in our work and supporting it. A website would provide them with a central source of information
- Glia team – The team currently spends a large amount of time manually managing volunteer and community requests. A better resource would free up our time to work on creative aspects of the project
Strategic partners
Ian Hamilton, Color Crate

Boundary players
- Potential collaborators such as academics, manufacturers and health care providers – These providers understand that Glia can help them, but may not be sure of how to contact the team or what our work entails. Ultimately, they are the main target audience of the website design
- Lay public – A website for the lay public would provide them with a central source of information
Methodology and activities
Design and Development
Through a consultative process, the website will be developed in collaboration with Glia's community manager (Carrie Wakem) and Color Crate's lead developer (Ian Hamilton). This process will involve input from the entire Glia team. The site will utilize WordPress for its content management, a leading open source software.
Deployment
Once the first complete version of the website is ready, it will be deployed via a DigitalOcean droplet running Ubuntu 16.04 server software and the NGINX web server.
Post-deployment assessment
To monitor performance of the site, we will use informal surveying of the team and incoming volunteers using a webform. As well, we will monitor before and after traffic using Mamoto (formerly Piwik), an open source web analytics software. If changes are needed, they will either be made by one of the Glia team or under contract by Mr. Hamilton.
Outputs and deliverables
Website
The primary deliverable of this project will be a new website (glia.org) running on a modern content management system (WordPress) on a new server (Ubuntu 16.04) on a DigitalOcean droplet with modern monitoring, backup and maintenance capabilities.
Reduction in time spent on community management
This will be difficult to quantify properly, however one of the main practical goals is to reduce the time spent by Carrie Wakem, Mohammed Abumatar and Tarek Loubani on responding to and managing community and volunteer requests. We hope to monitor this through continued formal time tracking and informal survey of the team.
Time frame
Six months. Start date is August 2018. Expected end date is May 2019.
Resources and budget

The cost as quoted by Color Crate for this website is USD$4,275.
Measures of success
What changes in behaviour do you expect to see?
We hope that stakeholders such as other academics, manufacturers and health care providers will be able to more easily find and share our work, resulting in a higher level of focused interest in our work.
What changes in behaviour would you like to see?
We would like to see the above stakeholders also use the website to respond to volunteer needs and targeted requests for help from the community.
What changes in behaviour would you love to see?
A stretch goal of this project would be to use the website to facilitate a community fundraiser such as via patreon or kickstarter.
Communication strategy
Intra-group communication will be done using Mattermost, Kanboard, email and in-person meetings.
External communication will be via twitter, facebook, instagram and public talks in Canada and internationally.
Sustainability strategy
The website will be maintained by Tarek Loubani, who has extensive experience securing, deploying and maintaining servers over many years. If needed, Ian Hamilton (Color Crate) will provide contract services.
Risks
There are two main risks for this project:
1. Misjudging the needs of the project website and providing information that is not required or not desired by the target audience. As such, the website would be an ornament rather than a usable tool. We are trying to mitigate this risk by spending a small amount of money and doing development that is guided by the needs we already have, rather than by a larger vision for needs that do not yet exist.
2. That the website quickly starts to decay and loses its utility and value in short order. This is very difficult to mitigate, but should be manageable by refreshing the site every 12-18 months in terms of content and design.