Project name
Pulse oximeter research and development
Fellows
Tarek Loubani, Luka Mustafa
Project update
The project has advanced significantly since work began with IRNAS. At this point, we have completed a significant part of the electronics and mechanics of the pulse oximeter.
Current prototypes are usable in ideal conditions, but not in adverse ones, and the reliability of the device is unacceptably low for use in critical patient care scenarios. Regulatory approval is still under way, but we haven’t yet received permission from Health Canada to use one critical part of our testing hardware (Respiract) to de-oxygenate test subjects in our calibration trial.
The time and cost overruns are multi-factorial, including overestimating the progress of the pre-existing pulse oximeter design, unexpected failures of the finger probe design, and difficulties in navigating regulatory hurdles for the first time.
Proposed changes
We have already overrun our budget, but have not yet completed engineering on the pulse oximeter. We would like IRNAS to continue mechanical and electronics work on the pulse oximeter until completion and believe that we have a much better idea of what this would require now. The main change in this proposal is the budget and time given to the engineering side of the project.

In terms of budget, we would like to increase the budget by USD$ 40,000 for engineering. This would be divided as follows. This table assumes that € 1 = USD$ 1.25, and that the cost per hour will remain as quoted by IRNAS as € 45.00:

	Hours	Total (€)
PulseOx finger clip improvement	200	9,000.00
Additional software development	208	9,360.00
Testing and calibration	180	8,100.00
Hardware improvement and redesign	120	7,200.00
Total	374	31,860.00

In terms of time, we request an extension of the completion date from June 2018 as presently approved until June 2019. This should account for any delays in engineering as well as regulatory approval.
Opportunity associated with change
The pulse oximeter is currently usable for some segments of the population (right finger size) in ideal conditions (sitting at rest, calm). This proposed change would allow us to complete the final parts of the engineering and polish the pulse oximeter so that it is usable not only in ideal conditions, but in adverse ones that might be faced by users in low-resource settings.
By allowing this proposed change and widening the conditions under which the pulse oximeter can be used, it will be possible to replace not only devices in ambulatory clinics, but also devices in emergency centres, ambulances and children’s clinics and hospitals. The current model does not currently permit these uses.
Risk associated with change
If forced to leave the pulse oximeter as is, we would contribute it to the literature and body of knowledge. Our excellent documentation and use of open source techniques makes our work a significant advancement that other groups could build upon.
However, the pulse oximeter would not be clinically useful in its current state, since it does not accommodate women or children due to small finger size. It also does not work well in agitated patients or those who are moving vigorously.
I fear that these limitations would so limit the pulse oximeter that a competent governmental buyer might overlook the value of the open source construction and potential to select other units that can be used on more patients out of the box.
Budget effect of change
This proposed change would increase the budget of this project by USD$ 40,000, paid to IRNAS. This amount would include some of the monies already paid to IRNAS from the Glia portion of the budget over the past several months.
Action required
No further action is required if this change is approved, as all relationships and contracts already exist and allow for cost overruns.